## Cost and Hours
Task Name | Work Hours | Typical Costs
Fiber Light Network Upgrade
Project Management
Develop a project plan | 12 | 780
Assign tasks to team members | 6 | 390
Manage the project timeline and schedule | 24 | 1560
Track project progress and milestones | 12 | 780
Communicate project updates to stakeholders | 6 | 390
Address project risks and issues | 12 | 780
Developing Office Space Infrastructure
Order furniture for 12 cubicles | 4 | 31420
Build cubicles that match the pre-existing Fiber Light theme | 80 | 4000
Remodel the old warehouse into a working space | 320 | 16000
Set up electrical wiring and outlets | 120 | 6000
Install lighting fixtures | 40 | 2000
Install HVAC system | 160 | 8000
Paint and decorate the walls | 40 | 2200
Procuring Hardware and Software Inventory
Research and select furniture supplier | 8 | 440
Procure 12 laptop computers with Windows 11 Enterprise and Microsoft Office 365 | 16 | 26380
Procure 12 VoIP handsets with PBX connectivity | 8 | 6980
Procure Kyocera multi-functional color network printer-copier with scanning and faxing ability | 8 | 5515
Purchase 16 Cat 6e cables | 8 | 830
Purchase Ciena 3926 aggregation switch | 8 | 3800
Installing and Setting up the Software and Hardware Devices
Unbox and set up the 12 laptop computers | 12 | 600
Connect the laptop computers to the network | 4 | 200
Install Windows 11 Enterprise and Microsoft Office 365 on the laptop computers | 24 | 1200
Connect the 12 VoIP handsets to the existing VoIP PBX phone system | 4 | 180
Configure the Kyocera multi-functional color network printer-copier | 8 | 360
Install and configure the Ciena 3926 aggregation switch | 16 | 720
Connect the Cat 6e cables to the cubicles and access points | 16 | 720
Run the cables from the access points to the data closet | 8 | 360
Connect the aggregation switch to the main server room router | 4 | 180
Quality Control and Testing
Test the network connectivity for all 12 cubicles | 8 | 340
Conduct quality checks on the furniture and inventory ordered | 8 | 340
Perform end-to-end connectivity tests | 16 | 680
Verify that all hardware and software devices are functioning properly | 8 | 340
Documentation and Training
Create user manuals for the hardware and software devices | 16 | 700
Document the network infrastructure and hardware configurations | 24 | 1050
Train the new employees on how to use the new hardware and software | 32 | 1400
Document project expenses and submit to accounting for tracking and billing purposes | 6 | 390
Total | 1106 | 128005